## By Date
| TO DO | START | DUE | RESPONSIBILITY | PORTFOLIO | CATEGORY | DEPENDENCY
0
NOVEMBER
x | Establish meeting schedule |  | 2021-11-16 | 0 | PM & Admin | Operations
x | prepare call for presentations graphics |  | 2021-11-22 | 0 | Program & Speakers | Communications
x | draft call for presentations eblast |  | 2021-11-22 | 0 | Program & Speakers | Communications
x | send branding content for translation |  | 2021-11-22 | 0 | Promotions & Collateral | Logistics
x | send call for presentations graphics, social media posts, eblast for translation |  | 2021-11-23 | 0 | Program & Speakers | Communications
x | determine program themes / topics for call for presentations |  | 2021-11-25 | 0 | Program & Speakers | Logistics
x | build call for presentations form & confirmation email |  | 2021-11-25 | 0 | Program & Speakers | Logistics
x | prepare call for presentations instructions & FAQ |  | 2021-11-25 | 0 | Program & Speakers | Communications
x | send call for presentations form, conf email, instructions, FAQ for translation |  | 2021-11-26 | 0 | Program & Speakers | Communications
0
DECEMBER
x | draft save the date email blast |  | 2021-12-01 | 0 | Promotions & Collateral | Communications
x | test call for presentations form | 2021-11-29 | 2021-12-02 | 0 | Program & Speakers | Logistics
x | Design branding / logo / theme |  | 2021-12-02 | 0 | Promotions & Collateral | Communications
x | Create social media hashtags |  | 2021-12-02 | 0 | Promotions & Collateral | Communications
x | send save the date email blast to translation |  | 2021-12-02 | 0 | Promotions & Collateral | Communications
| call for presentations opens |  | 2021-12-03 | 0 | Program & Speakers | milestone
x | draft call for presentations reminder eblast 1 |  | 2021-12-09 | 0 | Program & Speakers | Communications
x | send call for presentations reminder eblast 1, social media posts for translation |  | 2021-12-10 | 0 | Program & Speakers | Communications
x | submissions report |  | 2021-12-10 | 0 | Program & Speakers | Operations
x | Send Save the Date eblast and social meda |  | 2021-12-15 | 0 | Promotions & Collateral | Communications
x | submissions report |  | 2021-12-17 | 0 | Program & Speakers | Operations
x | draft call for presentations reminder eblast 2 |  | 2021-12-21 | 0 | Program & Speakers | Communications
x | send call for presentations reminder eblast 2, social media posts for translation |  | 2021-12-22 | 0 | Program & Speakers | Communications
x | call for presentations reminder - 1 |  | 2021-12-29 | 0 | Program & Speakers | Communications
x | submissions report |  | 2021-12-30 | 0 | Program & Speakers | Operations
0
JANUARY
x | call for presentations reminder - 2 |  | 2022-01-03 | 0 | Program & Speakers | Communications
x | Create budget | 2021-12-03 | 2022-01-03 | 0 | PM & Admin | Finance
x | call for presentations deadline |  | 2022-01-07 | 0 | Program & Speakers | milestone
x | send presentation submissions to committee for review |  | 2022-01-10 | 0 | Program & Speakers | Logistics
r | create speaker tracking sheet |  | 2022-01-10 | 0 | Program & Speakers | Logistics
x | select registration tool |  | 2022-01-10 | 0 | Registration | Registration
x | Book platform |  | 2022-01-10 | 0 | Logistics | Logistics
x | draft abstract acceptance/alternate/rejected notice |  | 2022-01-12 | 0 | Program & Speakers | Communications
x | send abstract acceptance/alternate/rejected notice to translation |  | 2022-01-13 | 0 | Program & Speakers | Communications
x | build registration form & confirmation email | 2022-01-10 | 2022-01-13 | 0 | Registration | Registration
x | send registration form & confirmation email to translation |  | 2022-01-13 | 0 | Registration | Logistics
x | draft registration open eblast, social media |  | 2022-01-14 | 0 | Registration | Communications
x | send registration open eblast, social media to translation |  | 2022-01-17 | 0 | Registration | Communications
x | prepare registration graphics |  | 2022-01-17 | 0 | Registration | Communications
x | send abstract acceptance/alternate/rejected notice |  | 2022-01-21 | 0 | Program & Speakers | Communications
x | draft registration reminder eblast 1 |  | 2022-01-21 | 0 | Registration | Communications
r | book interpreters |  | 2022-01-21 | 0 | Logistics | Logistics
x | test registration form | 2022-01-17 | 2022-01-24 | 0 | Registration | Logistics
x | send registration reminder eblast 1, social media posts for translation |  | 2022-01-24 | 0 | Registration | Communications
r | budget update |  | 2022-01-24 | 0 | PM & Admin | Finance
x | Registration Opens |  | 2022-01-25 | 0 | Registration | milestone
x | Determine staffing needs |  | 2022-01-25 | 0 | PM & Admin | Logistics
x | draft registration reminder eblast 2 |  | 2022-01-28 | 0 | Registration | Communications
x | speaker confirmation deadline |  | 2022-01-31 | 0 | Program & Speakers | milestone
r | create speaker kit | 2022-01-10 | 2022-01-31 | 0 | Program & Speakers | Logistics
r | create speaker portals | 2022-01-10 | 2022-01-31 | 0 | Program & Speakers | Logistics
r | schedule speaker orientations |  | 2022-01-31 | 0 | Program & Speakers | Logistics
x | send registration reminder eblast 2, social media posts for translation |  | 2022-01-31 | 0 | Registration | Communications
0
FEBRUARY
r | send session content, bios, etc for translation | 2022-01-10 | 2022-02-01 | 0 | Program & Speakers | Logistics
r | create preliminary program | 2022-01-10 | 2022-02-01 | 0 | Program & Speakers | Logistics
r | follow up unconfirmed presenters |  | 2022-02-01 | 0 | Program & Speakers | Logistics
r | finalize program | 2022-01-31 | 2022-02-01 | 0 | Program & Speakers | Logistics
r | program published to website |  | 2022-02-01 | 0 | Program & Speakers | Communications
r | registration reminder - 1 (program announcement) |  | 2022-02-02 | 0 | Registration | Communications
r | Send Registration Report |  | 2022-02-02 | 0 | Registration | Registration
r | Send Registration Report |  | 2022-02-02 | 0 | Registration | Registration
r | draft registration reminder eblast 3 |  | 2022-02-04 | 0 | Registration | Communications
r | send registration reminder eblast 3, social media posts for translation |  | 2022-02-07 | 0 | Registration | Communications
r | create production schedule |  | 2022-02-07 | 0 | Logistics | Logistics
r | create backstage Zoom links |  | 2022-02-08 | 0 | Program & Speakers | Logistics
r | send calendar invitations to speakers |  | 2022-02-08 | 0 | Program & Speakers | Communications
r | create interpreter Zoom links |  | 2022-02-08 | 0 | Logistics | Logistics
r | collect speaker bio, headshot | 2022-02-01 | 2022-02-09 | 0 | Program & Speakers | Logistics
r | registration reminder - 2 |  | 2022-02-09 | 0 | Registration | Communications
r | Send Registration Report |  | 2022-02-09 | 0 | Registration | Registration
r | budget update |  | 2022-02-09 | 0 | PM & Admin | Finance
r | Populate platform | 2022-01-10 | 2022-02-09 | 0 | Logistics | Logistics
r | create platform graphics | 2022-01-10 | 2022-02-09 | 0 | Logistics | Logistics
r | draft registration reminder eblast 4 |  | 2022-02-11 | 0 | Registration | Communications
r | draft Eblast to incomplete registrations re closing date |  | 2022-02-11 | 0 | Registration | Communications
r | prepare scripts |  | 2022-02-11 | 0 | Logistics | Logistics
r | send registration reminder eblast 4, social media posts for translation |  | 2022-02-14 | 0 | Registration | Communications
r | send Eblast to incomplete registrations re closing date to translation |  | 2022-02-14 | 0 | Registration | Communications
r | Send Registration Report |  | 2022-02-16 | 0 | Registration | Registration
r | registration reminder - 3 |  | 2022-02-16 | 0 | Registration | Communications
r | Draft Know Before You Go eblast(s) |  | 2022-02-17 | 0 | Registration | Communications
r | Prepare placeholder slides |  | 2022-02-18 | 0 | Promotions & Collateral | Logistics
r | draft thank you / follow-up eblasts |  | 2022-02-18 | 0 | Registration | Communications
r | Send Know Before You Go eblast(s) to translation |  | 2022-02-18 | 0 | Registration | Communications
r | Create attendee evaluation |  | 2022-02-18 | 0 | PM & Admin | Logistics
r | create speaker evaluation |  | 2022-02-18 | 0 | PM & Admin | Logistics
| Speaker Orientation | 2022-02-15 | 2022-02-21 | 0 | Program & Speakers | milestone
r | presentation decks, handouts due |  | 2022-02-22 | 0 | Program & Speakers | Logistics | do these need to be translated? If so we'll need to push this out 1-2 weeks
r | send thank you / follow-up eblasts to translation |  | 2022-02-22 | 0 | Registration | Communications
r | send evaluation forms to translation |  | 2022-02-22 | 0 | PM & Admin | Logistics
r | follow up presentation decks |  | 2022-02-23 | 0 | Program & Speakers | Logistics
r | Send Registration Report |  | 2022-02-23 | 0 | Registration | Registration
r | review incomplete records for duplication |  | 2022-02-23 | 0 | Registration | Registration
r | registration reminder - 4 |  | 2022-02-23 | 0 | Registration | Communications
r | send Eblast to incomplete registrations re closing date |  | 2022-02-23 | 0 | Registration | Communications
r | schedule push notifications |  | 2022-02-23 | 0 | Logistics | Logistics
r | collect speaker / chair / volunteer / etc cell numbers |  | 2022-02-24 | 0 | PM & Admin | Logistics
r | send slide decks and materials to interpreters |  | 2022-02-24 | 0 | Logistics | Logistics
r | budget update |  | 2022-02-25 | 0 | PM & Admin | Finance
r | draft final speaker info |  | 2022-02-28 | 0 | Program & Speakers | Communications
r | Upload registration list & send credentials |  | 2022-02-28 | 0 | Logistics | Registration
r | prepare attendee video tutorial | 2022-02-09 | 2022-02-28 | 0 | Logistics | Communications
r | pre-con with interpreters |  | 2022-02-28 | 0 | Logistics | Logistics
0
MARCH
r | send final speaker information with script | 2022-02-28 | 2022-03-02 | 0 | Program & Speakers | Communications
r | Send Know Before You Go eblast(s) | 2022-02-28 | 2022-03-02 | 0 | Registration | Communications
r | send thank you eblasts |  | 2022-03-03 | 0 | Registration | Communications
0
POST-EVENT
r | prepare speaker thank you notes |  | 2022-03-04 | 0 | Program & Speakers | Communications
r | send follow up eblast |  | 2022-03-07 | 0 | Registration | Communications
r | final registration report |  | 2022-03-09 | 0 | Registration | Operations
r | financial report / budget update with actuals |  | 2022-03-11 | 0 | PM & Admin | Finance
r | prepare evaulation summary reports | 2022-03-11 | 2022-03-18 | 0 | Program & Speakers | Communications
to add, insert row above this line

## By Portfolio
| TO DO | START | DUE | RESPONSIBILITY | PORTFOLIO | CATEGORY | DEPENDENCY
r | prepare call for presentations graphics |  | 2021-11-22 |  | Program & Speakers | Communications
r | draft call for presentations eblast |  | 2021-11-22 |  | Program & Speakers | Communications
r | send call for presentations graphics, social media posts, eblast for translation |  | 2021-11-23 |  | Program & Speakers | Communications
r | determine program themes / topics for call for presentations |  | 2021-11-25 |  | Program & Speakers | Logistics
r | build call for presentations form & confirmation email |  | 2021-11-25 |  | Program & Speakers | Logistics
r | prepare call for presentations instructions & FAQ |  | 2021-11-25 |  | Program & Speakers | Communications
r | send call for presentations form, conf email, instructions, FAQ for translation |  | 2021-11-26 |  | Program & Speakers | Communications
r | test call for presentations form | 2021-11-29 | 2021-12-02 |  | Program & Speakers | Logistics
r | draft call for presentations reminder eblast 1 |  | 2021-12-02 |  | Program & Speakers | Communications
| call for presentations opens |  | 2021-12-03 |  | Program & Speakers | milestone
r | send call for presentations reminder eblast 1, social media posts for translation |  | 2021-12-03 |  | Program & Speakers | Communications
r | draft call for presentations reminder eblast 2 |  | 2021-12-09 |  | Program & Speakers | Communications
r | send call for presentations reminder eblast 2, social media posts for translation |  | 2021-12-10 |  | Program & Speakers | Communications
r | submissions report |  | 2021-12-10 |  | Program & Speakers | Operations | repeats weekly
r | call for presentations reminder - 1 |  | 2021-12-13 |  | Program & Speakers | Communications
r | submissions report |  | 2021-12-17 |  | Program & Speakers | Operations | repeats weekly
r | draft call for presentations reminder eblast 3 |  | 2021-12-21 |  | Program & Speakers | Communications
r | send call for presentations reminder eblast 3, social media posts for translation |  | 2021-12-22 |  | Program & Speakers | Communications
r | call for presentations reminder - 2 |  | 2021-12-27 |  | Program & Speakers | Communications
r | submissions report |  | 2021-12-30 |  | Program & Speakers | Operations | repeats weekly
r | call for presentations reminder - 3 |  | 2022-01-03 |  | Program & Speakers | Communications
r | prepare presentations review instructions/kit |  | 2022-01-03 |  | Program & Speakers | Logistics
| call for presentations deadline |  | 2022-01-07 |  | Program & Speakers | milestone
r | send presentation submissions to committee for review |  | 2022-01-10 |  | Program & Speakers | Logistics
r | create speaker tracking sheet |  | 2022-01-10 |  | Program & Speakers | Logistics
r | draft abstract acceptance/alternate/rejected notice |  | 2022-01-12 |  | Program & Speakers | Communications
r | send abstract acceptance/alternate/rejected notice to translation |  | 2022-01-13 |  | Program & Speakers | Communications
r | send abstract acceptance/alternate/rejected notice |  | 2022-01-21 |  | Program & Speakers | Communications
| speaker confirmation deadline |  | 2022-01-31 |  | Program & Speakers | milestone
r | create speaker kit | 2022-01-10 | 2022-01-31 |  | Program & Speakers | Logistics
r | create speaker portals | 2022-01-10 | 2022-01-31 |  | Program & Speakers | Logistics
r | schedule speaker orientations |  | 2022-01-31 |  | Program & Speakers | Logistics
r | send session content, bios, etc for translation | 2022-01-10 | 2022-02-01 |  | Program & Speakers | Logistics
r | create preliminary program | 2022-01-10 | 2022-02-01 |  | Program & Speakers | Logistics
r | follow up unconfirmed presenters |  | 2022-02-01 |  | Program & Speakers | Logistics
r | finalize program | 2022-01-31 | 2022-02-01 |  | Program & Speakers | Logistics
r | program published to website |  | 2022-02-01 |  | Program & Speakers | Communications
r | create backstage Zoom links |  | 2022-02-08 |  | Program & Speakers | Logistics
r | send calendar invitations to speakers |  | 2022-02-08 |  | Program & Speakers | Communications
r | collect speaker bio, headshot | 2022-02-01 | 2022-02-09 |  | Program & Speakers | Logistics
| Speaker Orientation | 2022-02-15 | 2022-02-21 |  | Program & Speakers | milestone
r | presentation decks, handouts due |  | 2022-02-22 |  | Program & Speakers | Logistics | do these need to be translated? If so we'll need to push this out 1-2 weeks
r | follow up presentation decks |  | 2022-02-23 |  | Program & Speakers | Logistics
r | draft final speaker info |  | 2022-02-28 |  | Program & Speakers | Communications
r | send final speaker information with script | 2022-02-28 | 2022-03-02 |  | Program & Speakers | Communications
r | prepare speaker thank you notes |  | 2022-03-04 |  | Program & Speakers | Communications
r | prepare evaulation summary reports | 2022-03-11 | 2022-03-18 |  | Program & Speakers | Communications
r | send branding content for translation |  | 2021-11-22 |  | Promotions & Collateral | Logistics
r | draft save the date email blast |  | 2021-12-01 |  | Promotions & Collateral | Communications
r | Design branding / logo / theme |  | 2021-12-02 |  | Promotions & Collateral | Communications
r | Create social media hashtags |  | 2021-12-02 |  | Promotions & Collateral | Communications
r | send save the date email blast to translation |  | 2021-12-02 |  | Promotions & Collateral | Communications
r | Send Save the Date eblast and social meda |  | 2021-12-10 |  | Promotions & Collateral | Communications
r | Prepare placeholder slides |  | 2022-02-18 |  | Promotions & Collateral | Logistics
r | select registration tool |  | 2022-01-10 |  | Registration | Registration
r | build registration form & confirmation email | 2022-01-10 | 2022-01-13 |  | Registration | Registration
r | send registration form & confirmation email to translation |  | 2022-01-13 |  | Registration | Logistics
r | draft registration open eblast, social media |  | 2022-01-14 |  | Registration | Communications
r | send registration open eblast, social media to translation |  | 2022-01-17 |  | Registration | Communications
r | prepare registration graphics |  | 2022-01-17 |  | Registration | Communications
r | draft registration reminder eblast 1 |  | 2022-01-21 |  | Registration | Communications
r | test registration form | 2022-01-17 | 2022-01-24 |  | Registration | Logistics
r | send registration reminder eblast 1, social media posts for translation |  | 2022-01-24 |  | Registration | Communications
| Registration Opens |  | 2022-01-25 |  | Registration | milestone
r | draft registration reminder eblast 2 |  | 2022-01-28 |  | Registration | Communications
r | send registration reminder eblast 2, social media posts for translation |  | 2022-01-31 |  | Registration | Communications
r | registration reminder - 1 (program announcement) |  | 2022-02-02 |  | Registration | Communications
r | Send Registration Report |  | 2022-02-02 |  | Registration | Registration
r | Send Registration Report |  | 2022-02-02 |  | Registration | Registration
r | draft registration reminder eblast 3 |  | 2022-02-04 |  | Registration | Communications
r | send registration reminder eblast 3, social media posts for translation |  | 2022-02-07 |  | Registration | Communications
r | registration reminder - 2 |  | 2022-02-09 |  | Registration | Communications
r | Send Registration Report |  | 2022-02-09 |  | Registration | Registration
r | draft registration reminder eblast 4 |  | 2022-02-11 |  | Registration | Communications
r | draft Eblast to incomplete registrations re closing date |  | 2022-02-11 |  | Registration | Communications
r | send registration reminder eblast 4, social media posts for translation |  | 2022-02-14 |  | Registration | Communications
r | send Eblast to incomplete registrations re closing date to translation |  | 2022-02-14 |  | Registration | Communications
r | Send Registration Report |  | 2022-02-16 |  | Registration | Registration
r | registration reminder - 3 |  | 2022-02-16 |  | Registration | Communications
r | Draft Know Before You Go eblast(s) |  | 2022-02-17 |  | Registration | Communications
r | draft thank you / follow-up eblasts |  | 2022-02-18 |  | Registration | Communications
r | Send Know Before You Go eblast(s) to translation |  | 2022-02-18 |  | Registration | Communications
r | send thank you / follow-up eblasts to translation |  | 2022-02-22 |  | Registration | Communications
r | Send Registration Report |  | 2022-02-23 |  | Registration | Registration
r | review incomplete records for duplication |  | 2022-02-23 |  | Registration | Registration
r | registration reminder - 4 |  | 2022-02-23 |  | Registration | Communications
r | send Eblast to incomplete registrations re closing date |  | 2022-02-23 |  | Registration | Communications
r | Send Know Before You Go eblast(s) | 2022-02-28 | 2022-03-02 |  | Registration | Communications
r | send thank you eblasts |  | 2022-03-03 |  | Registration | Communications
r | send follow up eblast |  | 2022-03-07 |  | Registration | Communications
r | final registration report |  | 2022-03-09 |  | Registration | Operations
x | Establish meeting schedule |  | 2021-11-16 |  | PM & Admin | Operations
r | Create budget | 2021-12-03 | 2022-01-03 |  | PM & Admin | Finance
r | budget update |  | 2022-01-24 |  | PM & Admin | Finance
r | Determine staffing needs |  | 2022-01-25 |  | PM & Admin | Logistics
r | budget update |  | 2022-02-09 |  | PM & Admin | Finance
r | Create attendee evaluation |  | 2022-02-18 |  | PM & Admin | Logistics
r | create speaker evaluation |  | 2022-02-18 |  | PM & Admin | Logistics
r | send evaluation forms to translation |  | 2022-02-22 |  | PM & Admin | Logistics
r | collect speaker / chair / volunteer / etc cell numbers |  | 2022-02-24 |  | PM & Admin | Logistics
r | budget update |  | 2022-02-25 |  | PM & Admin | Finance
r | financial report / budget update with actuals |  | 2022-03-11 |  | PM & Admin | Finance
r | Book platform |  | 2022-01-10 |  | Logistics | Logistics
r | book interpreters |  | 2022-01-21 |  | Logistics | Logistics
r | create production schedule |  | 2022-02-07 |  | Logistics | Logistics
r | create interpreter Zoom links |  | 2022-02-08 |  | Logistics | Logistics
r | Populate platform | 2022-01-10 | 2022-02-09 |  | Logistics | Logistics
r | create platform graphics | 2022-01-10 | 2022-02-09 |  | Logistics | Logistics
r | prepare scripts |  | 2022-02-11 |  | Logistics | Logistics
r | schedule push notifications |  | 2022-02-23 |  | Logistics | Logistics
r | send slide decks and materials to interpreters |  | 2022-02-24 |  | Logistics | Logistics
r | Upload registration list & send credentials |  | 2022-02-28 |  | Logistics | Registration
r | prepare attendee video tutorial | 2022-02-09 | 2022-02-28 |  | Logistics | Communications
r | pre-con with interpreters |  | 2022-02-28 |  | Logistics | Logistics
to add, insert row above this line

## lists (hidden)
Portfolio | Category | Status
Activities & Events | Collateral | r
Exhibits | Communications | x
Logistics | Finance
Mobile App | Logistics | to add category, insert cell above black line
PM & Admin | Milestone
Program & Speakers | Operations
Promotions & Collateral | Registration
Registration
Sponsors | to add category, insert cell above black line
to add portfolio, insert cell above black line